## RESCO I
[11 empty] | Condition Precedent - Power Producer | [6 empty] | Condition Subsequent
Site Identification Number | PG | District | Developer | Category of Institution | Category of System | Estimated Capacity | LICA Signing Date | LICA acceptance Date (Dev) | CPBG Amount | CPBG Submission Date | PPA signing date | Survey Report | Finalised SPV Capacity | Inc / Dec % wrt estimated | SNA Capacity Approval Date | Revised CPBG submission Date Effective PPA date | Extension provided for CP Fulfilment | NM application submission date | Project layout Date | BoM Date | COD Milestone | Extension provided for CS Fulfilment | LD deduction start date | Accumulated LD for non compliance CS Fulfilment | Project Completion date | NM approval (for C1) | Advanced Subsidy Taken?
1 | A | D1 | Hero | Hospital | Net Metered | 317 | 2018-10-13 | 2018-10-19 | 792500 | 2018-10-29 | 2018-11-18 | 2018-12-18 | 337 | 6.309% | 2019-01-02 | 2019-01-12 | 0 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | 0 | 2019-03-13 |  | 2019-12-08 | 0 | 1
2 | A | D2 | Tepsol | College | Captive | 297 | 2018-10-12 | 2018-10-22 | 742500 | 2018-11-01 | 2018-11-25 | 2018-12-25 | 389 | 30.98% | 2019-01-09 | 2019-01-19 | 0 | 2019-03-20 | 2019-03-20 | 2019-03-20 | 2019-03-20 | 30 | 2019-04-19 |  | 2020-03-06 | 0 | 1
3 | B | D1 | Archita | Hospital | Net Metered | 278 | 2018-10-14 | 2018-10-22 | 695000 | 2018-11-03 | 2018-11-19 | 2018-12-19 | 217 | -21.94% | 2019-01-03 | 2018-11-19 | 0 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 0 | 2019-01-18 |  | 2019-10-01 | 1 | 0
4 | B | D3 | Hero | College | Captive | 75 | 2018-10-13 | 2018-10-22 | 187500 | 2018-11-04 | 2018-12-01 | 2018-12-31 | 69 | -8% | 2019-01-15 | 2018-12-01 | 0 | 2019-02-16 | 2019-02-16 | 2019-02-16 | 2019-02-16 | 0 | 2019-01-30 |  | 2019-11-18 | 0 | 0
5 | B | D3 | Tepsol | College | Captive | 116 | 2018-10-14 | 2018-10-28 | 290000 | 2018-11-04 | 2018-12-11 | 2019-01-10 | 148 | 27.59% | 2019-01-25 | 2019-02-04 | 0 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 30 | 2019-05-05 |  | 2020-04-25 | 0 | 0
6 | A | D1 | Archita | College | Net Metered | 118 | 2018-10-15 | 2018-10-25 | 295000 | 2018-11-04 | 2018-12-08 | 2019-01-07 | 157 | 33.05% | 2019-01-22 | 2019-02-01 | 0 | 2019-03-16 | 2019-03-16 | 2019-03-16 | 2019-03-16 | 0 | 2019-04-02 |  | 2019-12-26 | 0 | 1
7 | E | D1 | Hero | College | Captive | 364 | 2018-10-14 | 2018-10-20 | 910000 | 2018-10-29 | 2018-11-18 | 2018-12-18 | 504 | 38.46% | 2019-01-02 | 2019-01-12 | 12 | 2019-02-22 | 2019-02-22 | 2019-02-22 | 2019-02-22 | 60 | 2019-05-12 |  | 2020-02-27 | 0 | 0
8 | D | D3 | Tepsol | College | Net Metered | 377 | 2018-10-14 | 2018-10-29 | 942500 | 2018-11-12 | 2018-12-12 | 2019-01-11 | 409 | 8.488% | 2019-01-26 | 2019-02-05 | 0 | 2019-04-23 | 2019-04-23 | 2019-04-23 | 2019-04-23 | 0 | 2019-04-06 |  | 2020-02-13 | 1 | 0
9 | E | D3 | Archita | Hospital | Net Metered | 338 | 2018-10-11 | 2018-10-19 | 845000 | 2018-10-28 | 2018-11-18 | 2018-12-18 | 238 | -29.59% | 2019-01-02 | 2018-11-18 | 0 | 2019-01-12 | 2019-01-12 | 2019-01-12 | 2019-01-12 | 30 | 2019-02-16 |  | 2020-01-18 | 0 | 0
10 | E | D2 | Hero | College | Captive | 485 | 2018-10-10 | 2018-10-24 | 1212500 | 2018-11-01 | 2018-11-21 | 2018-12-21 | 398 | -17.94% | 2019-01-05 | 2018-11-21 | 15 | 2019-01-25 | 2019-01-25 | 2019-01-25 | 2019-01-25 | 60 | 2019-03-21 |  | 2019-11-27 | 0 | 1
11 | D | D2 | Tepsol | Hospital | Net Metered | 331 | 2018-10-12 | 2018-10-18 | 827500 | 2018-10-30 | 2018-11-15 | 2018-12-15 | 195 | -41.09% | 2018-12-30 | 2018-11-15 | 0 | 2018-12-27 | 2018-12-27 | 2018-12-27 | 2018-12-27 | 60 | 2019-03-15 |  | 2019-12-16 | 1 | 1
12 | F | D1 | Archita | Hospital | Captive | 99 | 2018-10-15 | 2018-10-24 | 247500 | 2018-10-31 | 2018-12-04 | 2019-01-03 | 130 | 31.31% | 2019-01-18 | 2019-01-28 | 0 | 2019-03-17 | 2019-03-17 | 2019-03-17 | 2019-03-17 | 60 | 2019-05-28 |  | 2020-03-11 | 0 | 0
13 | E | D3 | Hero | College | Net Metered | 399 | 2018-10-12 | 2018-10-18 | 997500 | 2018-10-28 | 2018-11-15 | 2018-12-15 | 338 | -15.29% | 2018-12-30 | 2018-11-15 | 0 | 2019-01-02 | 2019-01-02 | 2019-01-02 | 2019-01-02 | 0 | 2019-01-14 |  | 2019-12-04 | 0 | 1
14 | A | D1 | Tepsol | Hospital | Captive | 459 | 2018-10-10 | 2018-10-18 | 1147500 | 2018-11-02 | 2018-11-18 | 2018-12-18 | 409 | -10.89% | 2019-01-02 | 2018-11-18 | 0 | 2018-12-29 | 2018-12-29 | 2018-12-29 | 2018-12-29 | 0 | 2019-01-17 |  | 2019-10-02 | 0 | 0
2018-10-05
LD
SCOD key baad 5% , 9 months, 5% for 10 more weeks or cancel ppa and pay LD
CS delay, 2% upto 4 weeks then terminate
0.5% for every milestone, beyond 10 days
Formulas:
LICA acceptance Date (Dev) = [LICA Signing Date]+RANDBETWEEN(5,15)
CPBG Submission Date = [LICA acceptance Date (Dev)]+RANDBETWEEN(5,15)
PPA signing date = [LICA acceptance Date (Dev)]+RANDBETWEEN(25,50)
Survey Report = [PPA signing date]+30
SNA Capacity Approval Date = [Survey Report]+15
Project layout Date = [NM application submission date]
BoM Date = [Project layout Date]
COD Milestone = [BoM Date]
LD deduction start date = IF([Extension provided for CS Fulfilment]>0,Q3+[Extension provided for CS Fulfilment]+60,Q3+60)
Project Completion date = [LD deduction start date]+RANDBETWEEN(240,360)